## Slide 1
IBM QISKIT FALL FEST 2026
EVENT ORGANIZATION & OPERATION PLAN
End-to-End Operational Run-Book for In-Person & Online Hybrid Execution
Presented by IBM Quantum & Quantum for Humanity Org · November 16–20, 2026
📍 Venue: Bangalore, India (IST timezone) · 🌐 Virtual Hub: Discord Community Server
👥 Focus Areas: Registration Systems, Speaker Onboarding, AV Staging, and Hybrid Operations
Notes: Opening slide of the master organization plan for the Qiskit Fall Fest 2026. Briefly introduce the dual-presence structure (physical presence in Bangalore, India and virtual global hub on Discord) and align roles within the core committee.

## Slide 2
PRE-EVENT OPERATIONAL STRATEGY (MONTHS 1–3)
1. Attendee Onboarding & Registrations
• Launch official registration portal linking physical badges to virtual profiles.
• Collect T-shirt sizes, food/dietary preferences, and skill level.
• Auto-issue Discord invitation links upon successful registration validation.
2. Scaffolding Virtual Platforms
• Design Discord category architecture (Announcements, General, Ask-Mentors, Hack-Teams).
• Configure security verification bots to prevent server trolling and spam.
• Establish roles: Admin, Speaker, Mentor, Participant, Staff.
3. Speaker Consolidation (Resolving TBAs)
• Confirm travel itinerary and hotel accommodation for speakers traveling to Bangalore.
• Collect slide decks, custom code requirements, and speaker headshots.
• Execute green-room rehearsals for online streaming presenters.
4. Public Relations & Marketing
• Disseminate brand kit assets (flamingo, eagle, wave-function stickers) across social channels.
• Publish weekly countdown newsletters to the registered attendee database.
• Release official promotional videos detailing the Quantum for Humanity mission.
Notes: Pre-event strategy notes: Emphasize that registration is the primary pipeline of the operations. Focus on automating the onboarding of attendees into Discord and locking down speaker slide schedules weeks ahead.

## Slide 3
IN-PERSON VENUE OPERATIONS (BANGALORE HUB)
1. AV Staging & Staging Production
• Install dual 4K LED screens on stage with active fallback cabling.
• Deploy professional stage microphones (lapels for presenters, handhelds for Q&A).
• Set up a 3-cam video system: Cam 1 (Main presenter), Cam 2 (Wide stage), Cam 3 (Crowd Q&A).
• Ensure a hardware mixer is present for real-time noise suppression and audio feed splitting.
2. Registration Desks & Check-ins
• Set up 4 check-in queues: A-G, H-O, P-Z, and VIP/Speakers.
• Deploy QR barcode scanners to speed up physical badge printing.
• Distribute welcome kits (T-shirts, branded notebooks, sticker packs).
3. Local Hospitality & Logistics
• Partner with Bangalore transport providers for speaker airport pickups.
• Maintain strict dietary separation (Vegetarian, Vegan, Gluten-Free) at the catering tables.
• Set up hydration stations across the hall to eliminate single-use plastics.
4. Signage & Brand Environment
• Display QFF-2026 banners at the entrance, registration desks, and photo-booths.
• Install clear directional signage for the main hall, hackathon workspace, and catering zone.
• Set up an interactive 'Sticker Board' where students share custom sticker combinations.
Notes: In-person operations notes: Address physical layout. Ensure the staging system has active fallbacks. Mention that the registration process is the physical threshold—it must be fast and zero-friction.

## Slide 4
ONLINE STREAMING & DISCORD OPERATIONS
1. Hybrid Live Streaming Setup
• Stream raw AV output to YouTube Live / Twitch in 1080p60.
• Deploy hardware encoders (OBS Studio / vMix) to ingest physical cameras and virtual speaker feeds.
• Configure real-time overlay graphics with speaker names and the active session countdown timer.
2. Bridging In-Person & Online Audiences
• Assign a dedicated virtual host to monitor the YouTube Live and Discord chat channels.
• Virtual host acts as the voice of online participants during the Q&A sessions on the main stage.
• Stream live slides and code directly to Discord screenshares for remote teams.
3. Discord Operations & Security
• Secure channels using verified permissions and automatic link scanners.
• Program bots to trigger announcements before sessions start.
• Schedule virtual social activities (e.g. coffee rooms, icebreakers) to maintain high online engagement.
4. Digital Asset Distribution
• Link PDF handouts and Qiskit Jupyter Labs in the Discord resources channel.
• Automatically distribute digital certificates and QFF-26 credential badges using bot automation after attendance verification.
Notes: Online operations notes: Stream latency should be kept under 3 seconds. The Discord virtual host is a key role—without them, online participants will feel disconnected from the physical Bangalore crowd.

## Slide 5
THE 5-DAY OPERATIONAL BLUEPRINT
DAILY OPERATIONAL PHASES
• Day 1 (Mon, Nov 16) | Opening & Foundation
- Morning: In-person check-ins start at 8:00 AM IST.
- Keynote: Welcome address & roadmap release.
- Operational Task: Match and finalize hackathon teams in Discord.
• Day 2 (Tue, Nov 17) | Circuits & Algorithms
- Intermediate focus. Track Qiskit live code laboratories.
- Keynote: Eagle vs. Heron processor benchmarks.
- Operational Task: Collect and format code submissions for the open-source sprint.
• Day 3 (Wed, Nov 18) | Quantum for Humanity
- Applied/Impact focus. Local NGOs join panels.
- Topics: Climate modeling, agriculture, clean water.
- Operational Task: Moderate the responsibly-focused panels and record comments.
DAILY OPERATIONAL PHASES (CONT.)
• Day 4 (Thu, Nov 19) | Advanced Research & Quantum Safe
- Focus: Quantum error correction, VQE, and Quantum Safe.
- Operational Task: Run the corporate Masterclass.
- Midpoint Check-in: Host mentor matching slots (15-min reviews) for top hackathon teams.
• Day 5 (Fri, Nov 20) | Hackathon Finals & Closing
- Operational Task: Stream the final 10 hackathon team presentations.
- Award Ceremony: Tally judges' scoring cards and announce the IBM Quantum Prize winners.
- Closing: Launch the QfH Manifesto. Transition virtual participants to the final Discord celebration.
Notes: Daily blueprint notes: Run a tight morning check-in every day. Keep sessions on schedule. Focus on the transitions—such as moving from the Day 1 opening directly to the afternoon hackathon kickoff.

## Slide 6
HACKATHON OPERATIONAL MECHANICS
1. Team Formations & Submissions
• Open team registration on Day 1 (max 5 members per team).
• Form channels in Discord (e.g. #team-01, #team-02) dynamically via bot allocation.
• Provide teams with sandbox IBM Quantum access keys and pre-configured Qiskit notebook templates.
• Enforce a strict submission deadline on Day 4 at 12:00 PM IST (GitHub repo URLs).
2. Onboarding Mentors & Advisors
• Secure 15 IBM Quantum researchers to serve as technical mentors.
• Establish mentor channels in Discord with ping bots to triage student questions.
3. Jury Onboarding & Scoring Matrix
• Onboard a 5-member jury panel consisting of academic, IBM, and industry experts.
• Standardize the scoring sheet on a 100-point rubric:
- 30 pts: Technical depth of the Qiskit code.
- 30 pts: Novelty and impact of the humanitarian solution.
- 20 pts: Presentation clarity and slide deck visual quality.
- 20 pts: Code documentation and reproducibility.
4. Live Finals Production
• Select top 10 teams to present on Day 5.
• Allocate 5 minutes for presentation and 3 minutes for Q&A.
Notes: Hackathon operations notes: Keep a strict submission deadline—the system must automatically close GitHub PRs. Tally the scorecards in a shared Google Sheet in real-time to avoid award ceremony delays.

## Slide 7
WEBSITE UPDATE: RESOLVING TBA SPEAKERS
OUTLINING CURRENT WEBPAGE VULNERABILITIES
• The live QFF-26 index.html contains 8 placeholders marked as 'Speaker TBA'.
• Over 27 cells in the program schedule table are marked as 'TBD' for presenter names.
• To make this plan completely ready for execution, we propose concrete, highly-aligned expert profiles to update the website immediately:
1. Opening Keynote Presenter
- Sourced: IBM Fellow & VP of IBM Quantum.
- Topic: Quantum Roadmap 2026.
2. Quantum Error Correction (QEC) Presenter
- Sourced: Lead QEC Researcher, IBM.
- Topic: Scaling Surface Codes.
PROPOSED EXPERTS TO SOLVE SCHEDULE HOLES
3. Quantum Machine Learning (QML) Academic
- Sourced: Lead AI & QML Professor, IIT Madras.
- Topic: Quantum Kernels and Neural Networks.
4. Quantum for Humanity Presenter
- Sourced: Executive Director, QfH Organization.
- Topic: Scaling Open Science for Global Good.
5. Quantum Chemistry Presenter
- Sourced: Materials Scientist, IISc Bangalore.
- Topic: Nitrogen Fixation and Molecular Simulation.
6. IBM Hardware Presenter
- Sourced: Chief Hardware Architect, IBM.
- Topic: Heron vs. Eagle Coherence Milestones.
Notes: Website updates notes: Detail the need to replace 'TBA' and 'TBD' placeholders on the web pages with real, prestigious profiles to build visitor credibility and drive registration numbers.

## Slide 8
POST-EVENT METRICS & ARCHIVING OPERATIONS
1. Media Post-Production
• Edit and cut live stream videos into individual session talks within 48 hours.
• Publish edited lectures to YouTube and link them in the Qiskit study materials.
• Create and publish a 3-minute highlight reel capturing main stage energy, hackathon project sprints, and local student testimonials.
2. Participant Certifications
• Verify final student participation records from physical scan logs and Discord presence.
• Auto-issue IBM Qiskit Fall Fest badges and Quantum Safe certificate files via email.
3. Impact Assessment & Reporting
• Consolidate hackathon output repos and draft the 'Global Projects Report'.
• Calculate and publish event metrics (number of attendees, projects, codes compiled).
• Send out attendee feedback surveys to assess logistics and workshop clarity.
4. Continuing Engagement
• Keep Discord server open as an ongoing Qiskit study forum.
• Host monthly virtual follow-up meetups with hackathon winners.
• Set up registration notifications for QFF-2027.
Notes: Post-event metrics notes: Make sure the digital badges are dispatched instantly. Highlight continuing engagement—keeping the Discord community alive is essential for lasting educational impact.

## Slide 9
COMPREHENSIVE BUDGET ESTIMATES
Estimated Core Budget for Physical Hub & Online Streaming Production:
• Physical Venue & Hospitality (50%):
- Auditorium Rental (5 Days, Bangalore Hub): $15,000
- Catering (Lunch, High-Tea, Coffee for 200 participants daily): $12,500
- Speaker Hotel Accommodations & Air Travel: $8,000
• Staging AV & Digital Production (25%):
- Dual 4K LED Screen Rental, Cam rigs, Lapel and Q&A mic arrays: $7,000
- Dedicated high-bandwidth internet line, live stream switching gear: $3,000
- Video editor post-production and highlight reel cuts: $2,500
• Collateral & Attendee Onboarding (15%):
- Participant welcome kits (T-shirts, branded diaries, stickers): $6,000
- Physical badges, lanyards, poster boards, directional banners: $2,000
• Marketing, Operations & Emergency Fallback (10%):
- Paid PR, social newsletters, emergency backups, local security: $4,000
- TOTAL BUDGET ESTIMATE: $60,000 (Funded by IBM Quantum & Sponsors)
Notes: Budget notes: Walk through the main chunks of costs. Detail that venue hospitality represents half of the allocation, and professional AV staging is essential for successful hybrid streaming.

## Slide 10
OPERATIONAL TIMELINE & MILESTONES
Operational Checkpoint Milestones leading to November 16 Launch:
• Milestone 1 | Pre-Event - Weeks 10-12 (T-10 Weeks):
- Partner agreements finalized. Budget approved.
- Website index.html live with registration links. Discord scaffold structures built.
• Milestone 2 | Pre-Event - Weeks 4-6 (T-4 Weeks):
- Confirm and lock in all 8 keynote speakers and replace webpage 'TBA' cards.
- AV contract signed. Bangalore venue logistics checked. Welcome kits ordered.
• Milestone 3 | Pre-Event - Weeks 1-2 (T-1 Week):
- Complete test stream run. Setup verified secure Discord bots. Badge roster loaded.
- Rehearsals completed for virtual and physical hosts. Speaker presentations compiled.
• Milestone 4 | Live Event Week:
- In-person and online gates open at 8:00 AM IST. Daily run-sheets enforced.
• Milestone 5 | Post-Event + 1 Week:
- Distribute certificates. Publish edited session videos. Launch QfH Manifesto.
Notes: Closing milestone notes: Go over the timeline checkpoints. Emphasize that the first major milestone is locking down agreements, and the critical pre-event check is verifying live streams and onboarding speakers.